## Feature Inventory
Feature ID | Module | Stage | Feature | What It Does | Phase | Priority (MoSCoW) | Complexity (S/M/L) | Effort Estimate (Person-Days) | Effort Estimate (Person-Hours) | Effort Estimate w/ Claude AI Assistance (Person-Days) | Effort Estimate w/ Claude AI Assistance (Person-Hours) | Notes
|  |  | Authentication & Authorization | Login, AD authentication and User access matrix | 1 |  | S |  | 80 |  | 56
|  |  | Notification Module | Email notification, In App notification | 1 |  | L |  | 160 |  | 120
F-001 | Module 1 - Procurement | Define & Plan | Create Project | Register a new vehicle programme / project so downstream parts, suppliers and cost records have somewhere to attach. | 1 | Must | M | 5 | 40 | 3 | 24
F-002 | Module 1 - Procurement | Define & Plan | Upload BOM & Part List | Bulk-load the parts list and BOM lines for a project ahead of sourcing. | 1 | Must | L | 12 | 96 | 7 | 56
F-003 | Module 1 - Procurement | Define & Plan | Maintain Master Data (Project, Part, Supplier, Commodity, FX) | Single screen/entry point for all core masters used across the platform. | 1 | Must | L | 15 | 120 | 8 | 64
F-004 | Module 1 - Procurement | Define & Plan | Define Commodity & Exchange Rate | Set up commodity items and FX rates that CBD and pricing calculations will reference. | 1 | Must | M | 6 | 48 | 3 | 24
F-005 | Module 1 - Procurement | Define & Plan | Define Milestones & Targets | Set the project-level milestone plan (dates/targets) that SRM and Technical Change later track against. | 1 | Must | L | 10 | 80 | 7 | 56
F-006 | Module 1 - Procurement | Source & Nominate | Import Sourcing Report (EBON+) | Ingest the Sourcing Report (Excel, 85 columns) for decided sourcing at defined intervals; system parses and updates the database. | 1 | Must | L | 18 | 144 | 11 | 88
F-007 | Module 1 - Procurement | Source & Nominate | RFQ Management | Track Request-for-Quotation issuance to shortlisted suppliers. | 1 | Should | M | 7 | 56 | 5 | 40
F-008 | Module 1 - Procurement | Source & Nominate | Supplier Quotations | Capture supplier-submitted quotes against an RFQ. | 1 | Should | M | 6 | 48 | 4 | 32
F-009 | Module 1 - Procurement | Source & Nominate | Supplier Comparison | Side-by-side comparison view of competing supplier quotes. | 1 | Should | S | 4 | 32 | 2 | 16
F-010 | Module 1 - Procurement | Source & Nominate | Supplier Nomination | Formally nominate the winning supplier for a part. | 1 | Must | M | 5 | 40 | 3 | 24
F-011 | Module 1 - Procurement | Source & Nominate | Commercial Negotiation | Record negotiation rounds and final agreed terms before CBD lock. | 1 | Must | M | 6 | 48 | 4 | 32
F-012 | Module 1 - Procurement | Commercial Management | Cost Breakdown (CBD) | Capture the full cost structure per part: quantity/car, weights (Steel/Alu/Cu/Pb/Precious, gross+net), import content & FX, VSI, Target, D&D amortisation. | 1 | Must | L | 18 | 144 | 13 | 104
F-013 | Module 1 - Procurement | Commercial Management | Price Tracking & History | Maintain full price version history per part — no silent overwrites. | 1 | Must | M | 7 | 56 | 4 | 32
F-014 | Module 1 - Procurement | Commercial Management | Investment Cost | Track tooling/CAPEX cost per part, linked to Tooling Master. | 1 | Must | M | 6 | 48 | 3 | 24
F-015 | Module 1 - Procurement | Commercial Management | Tooling Cost | Capture supplier CAPEX and cost amortisation for tooling. | 1 | Must | M | 6 | 48 | 3 | 24
F-016 | Module 1 - Procurement | Commercial Management | Commodity Prices | Maintain live commodity rates feeding automatic price recalculation. | 1 | Must | M | 6 | 48 | 3 | 24
F-017 | Module 1 - Procurement | Commercial Management | Forex Impact | Capture FX exposure and rate effective dates per project/sourcing. | 1 | Must | M | 6 | 48 | 3 | 24
F-018 | Module 1 - Procurement | Commercial Management | Target Cost | Record the original target cost (VSI Target) per part for variance tracking. | 1 | Must | M | 5 | 40 | 3 | 24
F-019 | Module 1 - Procurement | Commercial Management | Business Share Allocation | Track supplier's share of total part volume/business. | 1 | Should | M | 5 | 40 | 3 | 24
F-020 | Module 1 - Procurement | Commercial Management | BOM Cost Rollup | Aggregate part-level costs up to car/BOM level for total material cost. | 1 | Must | L | 12 | 96 | 8 | 64
F-021 | Module 1 - Procurement | Approve & Execute | Commercial Approval | Approve negotiated price/CBD before it becomes active. | 1 | Must | M | 6 | 48 | 4 | 32
F-022 | Module 1 - Procurement | Approve & Execute | Commodity Approval | Approve commodity price updates before they feed automatic recalculation. | 1 | Must | M | 5 | 40 | 3 | 24
F-023 | Module 1 - Procurement | Approve & Execute | Management Approval | Escalation-level approval for high-value or high-risk changes. | 1 | Must | M | 5 | 40 | 3 | 24
F-024 | Module 1 - Procurement | Approve & Execute | PO Creation | Generate or update Purchase Orders (EBON) from approved commercial terms. | 1 | Must | L | 10 | 80 | 7 | 56
F-025 | Module 1 - Procurement | Approve & Execute | PO Tracking | Track PO status from creation through supplier acknowledgement. | 1 | Should | M | 6 | 48 | 3 | 24
F-026 | Module 1 - Procurement | Approve & Execute | Notifications & Alerts | Notify users of pending actions — as both email and an in-app task. | 1 | Must | S | 4 | 32 | 2 | 16
F-027 | Module 1 - Procurement | Approve & Execute | Escalations | Escalate overdue approvals/actions per the defined ladder. | 1 | Must | M | 6 | 48 | 4 | 32
F-028 | Module 1 - Procurement | Approve & Execute | Audit Trail | Full change/approval history retained against every workflow number. | 1 | Must | S | 4 | 32 | 2 | 16
F-029 | Module 1 - Procurement | Analyse & Optimise | Material Cost Dashboard | Cost walk (BG vs FC) with Procurement and Finance/Controlling views, brand-aware across all 6 VW Group brands. | 1 | Must | M | 8 | 64 | 5 | 40
F-030 | Module 1 - Procurement | Analyse & Optimise | Investment Dashboard | Tooling/CAPEX cost visibility across active projects. | 1 | Must | M | 7 | 56 | 4 | 32
F-031 | Module 1 - Procurement | Analyse & Optimise | Benchmarking Dashboard | Compare cost/investment data against uploaded external/other-project benchmarks. | 1 | Must | S | 5 | 40 | 3 | 24
F-032 | Module 1 - Procurement | Analyse & Optimise | AI Chatbot (Q&A) | Natural-language query for Material Cost and Tooling/Readiness, at Part or Car level, text + graphical. | 1 | Must | L | 25 | 200 | 18 | 144
F-033 | Module 1 - Procurement | Analyse & Optimise | Commodity Forecasting | Directional forecast for commodity/forex risk and savings potential (steel specifically called out). | 3 | Must | L | 20 | 160 | 14 | 112
F-034 | Module 1 - Procurement | Analyse & Optimise | Cost Saving Opportunities | AI-surfaced savings opportunities from price/commodity trend analysis. | 1 | Could | L | 18 | 144 | 13 | 104
F-035 | Module 1 - Procurement | Analyse & Optimise | Automated Reports (PPT/PDF/Excel) | Generate the Material Cost Review and other reports from live data on demand. | 1 | Must | L | 12 | 96 | 7 | 56
F-036 | Module 1 - Procurement | Analyse & Optimise | Executive Summary | One-page management rollup view across cost, savings, and risk. | 1 | Could | M | 6 | 48 | 4 | 32
F-037 | Procurement Orders | General | Component-Level Hierarchy Mapping | Map every requirement to Car → Plant → Model/Variant → System → Assembly → Component Level. | 1 | Must | L | 14 | 112 | 10 | 80
F-038 | Procurement Orders | General | Requirement-Raising Workflow | Raise a new requirement linked to an existing Part/Tool master, or flag as new-part-pending-creation. | 1 | Must | M | 6 | 48 | 4 | 32
F-039 | Procurement Orders | General | Fulfilment Status Tracker | Track requirement status: raised → technical review → sourcing → PO release → production → delivery. | 1 | Must | M | 6 | 48 | 4 | 32
F-040 | Procurement Orders | General | Cross-Module Linking | Link a requirement to its related Change Request and/or SRM milestone. | 1 | Must | L | 8 | 64 | 5 | 40
F-041 | Module 2 - Technical Change | Change Initiation | Create Change (AEKO / AWE / AeA / Running Change / MY Change / Supplier Proposal) | Raise a new technical change of any recognised type. | 2 | Should | M | 7 | 56 | 5 | 40
F-042 | Module 2 - Technical Change | Change Initiation | Upload Documents (PDF / Excel / Drawings) | Attach the source change documents. | 2 | Must | M | 5 | 40 | 3 | 24
F-043 | Module 2 - Technical Change | Change Initiation | AI Document Processing & Auto-Extraction | System reads the uploaded PDF/Excel and drafts the Evaluation Sheet automatically. | 2 | Must | L | 22 | 176 | 15 | 120
F-044 | Module 2 - Technical Change | Change Initiation | System Generates Change ID & Workflow No. | Every change gets a unique, auditable identifier the moment it's created. | 2 | Must | M | 3 | 24 | 2 | 16
F-045 | Module 2 - Technical Change | Validation & Triage | Automatic Data Validation | System checks the uploaded change against master data before it proceeds. | 2 | Should | S | 4 | 32 | 2 | 16
F-046 | Module 2 - Technical Change | Validation & Triage | Check Project, Part, Supplier, BOM, Price, Revision | Cross-reference the change against current master records for consistency. | 2 | Must | S | 4 | 32 | 2 | 16
F-047 | Module 2 - Technical Change | Validation & Triage | Assign Buyer, SRM Engineer, Engineering Owner, Approver | Route the validated change to the right people for evaluation. | 2 | Must | S | 4 | 32 | 2 | 16
F-048 | Module 2 - Technical Change | Validation & Triage | Return for Correction if Validation Fails | Send the change back to its initiator with the reason, rather than silently blocking it. | 2 | Should | M | 4 | 32 | 3 | 24
F-049 | Module 2 - Technical Change | Impact Analysis | Commercial Impact | Quantify the price/cost impact of the proposed change. | 2 | Must | L | 10 | 80 | 7 | 56
F-050 | Module 2 - Technical Change | Impact Analysis | Technical Impact | Assess engineering/design consequences of the change. | 2 | Should | M | 6 | 48 | 4 | 32
F-051 | Module 2 - Technical Change | Impact Analysis | Supply Chain Impact | Assess effect on sourcing, lead time, and supplier capacity. | 2 | Should | M | 6 | 48 | 4 | 32
F-052 | Module 2 - Technical Change | Impact Analysis | Production Impact | Assess effect on plant production line/process. | 2 | Should | M | 6 | 48 | 4 | 32
F-053 | Module 2 - Technical Change | Impact Analysis | Cost Analysis & Savings / Increase | Net cost impact calculation — savings or increase — versus current price. | 2 | Must | M | 7 | 56 | 5 | 40
F-054 | Module 2 - Technical Change | Impact Analysis | AI Insights: Similar Changes, Risk Prediction | Surface historically similar changes and flag risk indicators for this one. | 3 | Could | L | 20 | 160 | 14 | 112
F-055 | Module 2 - Technical Change | Supplier Evaluation | Send Change Package to Supplier | Buyer downloads the necessary details and sends them to the supplier for evaluation. | 2 | Must | M | 5 | 40 | 3 | 24
F-056 | Module 2 - Technical Change | Supplier Evaluation | Supplier Submits Offer, Timeline, Investment, Tooling, Capacity | Supplier's full commercial and capability response to the change. | 2 | Must | M | 7 | 56 | 5 | 40
F-057 | Module 2 - Technical Change | Supplier Evaluation | Upload Supporting Documents | Attach the supplier's supporting evidence/quotes. | 2 | Must | M | 4 | 32 | 2 | 16
F-058 | Module 2 - Technical Change | Supplier Evaluation | Buyer Review & Clarification Loop | Buyer reviews the offer and can loop back to the supplier for clarification before locking it. | 2 | Should | M | 6 | 48 | 4 | 32
F-059 | Module 2 - Technical Change | Supplier Evaluation | Final Offer Locked | Offer is finalised and cannot be silently altered afterward. | 2 | Must | L | 6 | 48 | 4 | 32
F-060 | Module 2 - Technical Change | Approval Workflow | Engineering Approval | Sign-off from Engineering on the technical aspects of the change. | 2 | Must | M | 5 | 40 | 3 | 24
F-061 | Module 2 - Technical Change | Approval Workflow | Quality Approval | Sign-off from Quality. | 2 | Must | M | 5 | 40 | 3 | 24
F-062 | Module 2 - Technical Change | Approval Workflow | SRM Approval | Sign-off from SRM — relevant if the change affects tooling/milestones. | 2 | Must | L | 6 | 48 | 4 | 32
F-063 | Module 2 - Technical Change | Approval Workflow | Finance Approval | Sign-off from Finance on commercial impact. | 2 | Must | M | 5 | 40 | 3 | 24
F-064 | Module 2 - Technical Change | Approval Workflow | Commodity Approval | Sign-off from Commodity Lead if commodity pricing is affected. | 2 | Must | M | 5 | 40 | 3 | 24
F-065 | Module 2 - Technical Change | Approval Workflow | Management Approval | Final escalation-level sign-off for high-impact changes. | 2 | Must | M | 5 | 40 | 3 | 24
F-066 | Module 2 - Technical Change | Approval Workflow | Digital Signatures, Comments & Version Control | Each approval stage is signed, commented, and versioned for audit. | 2 | Should | L | 12 | 96 | 10 | 80
F-067 | Module 2 - Technical Change | Implementation & Control | ERP / Price Update | Push the approved new price into EBON/ERP records. | 2 | Must | L | 12 | 96 | 8 | 64
F-068 | Module 2 - Technical Change | Implementation & Control | Supplier Notification | Notify the supplier the change is approved and active. | 2 | Must | S | 3 | 24 | 2 | 16
F-069 | Module 2 - Technical Change | Implementation & Control | Drawing Release | Release the updated engineering drawing tied to the change. | 2 | Should | M | 5 | 40 | 3 | 24
F-070 | Module 2 - Technical Change | Implementation & Control | Tool Order | Trigger a new/updated tool order if the change requires one. | 2 | Should | M | 6 | 48 | 4 | 32
F-071 | Module 2 - Technical Change | Implementation & Control | BOM / PO Update | Update BOM and any open Purchase Orders to reflect the change. | 2 | Must | M | 7 | 56 | 5 | 40
F-072 | Module 2 - Technical Change | Implementation & Control | Plant / Quality / Production Notification | Notify downstream plant stakeholders that the change is live. | 2 | Should | S | 3 | 24 | 2 | 16
F-073 | Module 2 - Technical Change | Implementation & Control | Monitor & Track Implementation | Confirm the change has been implemented as approved. | 2 | Must | M | 6 | 48 | 4 | 32
F-074 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Change Dashboard (Open / Pending / Approved) | Live status view of all changes by state. | 2 | Must | M | 7 | 56 | 4 | 32
F-075 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | AI Chatbot (Queries, Status, Cost Impact) | Ask the assistant about any change's status or cost impact. | 2 | Must | L | 16 | 128 | 11 | 88
F-076 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Reports & PPT (Excel / PowerPoint / PDF) | Downloadable reports for management circulation. | 2 | Must | M | 8 | 64 | 5 | 40
F-077 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Change History & Audit Trail | Full, immutable history of every change and its approvals. | 2 | Must | S | 4 | 32 | 2 | 16
F-078 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Cost Impact & Savings Analysis | Aggregate view of net cost impact across all changes. | 2 | Must | M | 7 | 56 | 5 | 40
F-079 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Risk Forecasting (Delay, Cost, Supplier Risk) | AI-based prediction of likely delay/cost/supplier risk for open changes. | 3 | Could | L | 18 | 144 | 13 | 104
F-080 | Module 3 - SRM | Part Assignment | Create SRM Project | Set up a new SRM tracking project, typically aligned to a Project Master record. | 1 | Must | M | 5 | 40 | 3 | 24
F-081 | Module 3 - SRM | Part Assignment | Import Parts & BOM | Bring in the parts/BOM that need SRM tracking for this project. | 1 | Must | M | 7 | 56 | 4 | 32
F-082 | Module 3 - SRM | Part Assignment | Import Supplier List | Bring in the suppliers responsible for these parts. | 1 | Must | M | 6 | 48 | 4 | 32
F-083 | Module 3 - SRM | Part Assignment | Assign KTM Expert | Assign the KTM-level expert responsible for oversight. | 1 | Must | S | 3 | 24 | 2 | 16
F-084 | Module 3 - SRM | Part Assignment | Assign QE, Buyer, SRM Engineer, Logistics, Tool Owner | Assign all the named stakeholders for this part's readiness tracking. | 1 | Must | S | 4 | 32 | 2 | 16
F-085 | Module 3 - SRM | Part Assignment | Define Milestones | Set the milestone plan (from the 19-stage set) for this part. | 1 | Must | L | 9 | 72 | 6 | 48
F-086 | Module 3 - SRM | Part Assignment | Start Monitoring | Activate tracking — reminders and alerts begin from this point. | 1 | Must | S | 3 | 24 | 2 | 16
F-087 | Module 3 - SRM | Supplier Onboarding | Supplier Master Data | Core supplier record — code, name, location, category. | 1 | Must | S | 4 | 32 | 2 | 16
F-088 | Module 3 - SRM | Supplier Onboarding | Plant, Contacts, Tool Shop | Supplier's plant address, key contacts, and tool-shop details. | 1 | Should | M | 5 | 40 | 3 | 24
F-089 | Module 3 - SRM | Supplier Onboarding | Tool Maker & Cavities | Identify who makes the tool and how many cavities it has. | 1 | Must | M | 4 | 32 | 2 | 16
F-090 | Module 3 - SRM | Supplier Onboarding | Capacity, Location, Certifications | Supplier's production capacity, plant location, and quality certifications. | 1 | Should | M | 5 | 40 | 3 | 24
F-091 | Module 3 - SRM | Supplier Onboarding | Commodity, Business Share | Which commodity the supplier covers and their share of business. | 1 | Should | M | 4 | 32 | 2 | 16
F-092 | Module 3 - SRM | Supplier Onboarding | Risk Rating & Performance | Ongoing supplier risk/performance score. | 1 | Should | L | 9 | 72 | 6 | 48
F-093 | Module 3 - SRM | Tool Readiness | Tool Number, Type, Location | Core tool identity and where it currently sits. | 1 | Must | S | 3 | 24 | 2 | 16
F-094 | Module 3 - SRM | Tool Readiness | Tool Maker & Cavities | As captured at onboarding, tracked through the tool's life. | 1 | Must | M | 4 | 32 | 2 | 16
F-095 | Module 3 - SRM | Tool Readiness | Tool Kickoff | Record when tool development formally begins. | 1 | Must | L | 6 | 48 | 4 | 32
F-096 | Module 3 - SRM | Tool Readiness | Tool Trial | Record trial runs and outcomes. | 1 | Must | M | 5 | 40 | 3 | 24
F-097 | Module 3 - SRM | Tool Readiness | Tool Investment & Completion % | Track CAPEX spend against percentage complete. | 1 | Must | M | 6 | 48 | 3 | 24
F-098 | Module 3 - SRM | Tool Readiness | Tool Trial & Shipment Status | Status of trial completion and shipment to series site. | 1 | Must | L | 7 | 56 | 5 | 40
F-099 | Module 3 - SRM | Tool Readiness | First Parts | Record of first parts produced off the tool. | 1 | Must | L | 6 | 48 | 3 | 24
F-100 | Module 3 - SRM | Tool Readiness | Tool Photos & Maintenance | Photographic record and maintenance log for the tool. | 1 | Must | S | 4 | 32 | 2 | 16
F-101 | Module 3 - SRM | Milestone Tracking | B Release | One of the 19 confirmed milestone stages. | 1 | Must | L | 6 | 48 | 3 | 24
F-102 | Module 3 - SRM | Milestone Tracking | P-Frei / B-Frei | Release-freeze milestone pair. | 1 | Must | L | 6 | 48 | 3 | 24
F-103 | Module 3 - SRM | Milestone Tracking | VFF → PVS → 0-Series | Core pre-series milestone chain. | 1 | Must | L | 8 | 64 | 5 | 40
F-104 | Module 3 - SRM | Milestone Tracking | PPAP → SOP Readiness → SOP | Final approval-to-production milestone chain. | 1 | Must | L | 8 | 64 | 5 | 40
F-105 | Module 3 - SRM | Readiness Assessment | Engineering | Readiness score for the engineering dimension. | 1 | Should | L | 6 | 48 | 3 | 24
F-106 | Module 3 - SRM | Readiness Assessment | Quality | Readiness score for the quality dimension. | 1 | Should | M | 5 | 40 | 3 | 24
F-107 | Module 3 - SRM | Readiness Assessment | Tooling | Readiness score for tooling. | 1 | Must | M | 5 | 40 | 3 | 24
F-108 | Module 3 - SRM | Readiness Assessment | Capacity | Readiness score for supplier production capacity. | 1 | Should | M | 5 | 40 | 3 | 24
F-109 | Module 3 - SRM | Readiness Assessment | Material | Readiness score for material availability. | 1 | Should | M | 5 | 40 | 3 | 24
F-110 | Module 3 - SRM | Readiness Assessment | Logistics | Readiness score for logistics/delivery. | 1 | Should | M | 5 | 40 | 3 | 24
F-111 | Module 3 - SRM | Readiness Assessment | Production | Readiness score for production-line readiness. | 1 | Should | M | 5 | 40 | 3 | 24
F-112 | Module 3 - SRM | Readiness Assessment | Overall Readiness Score (R/Y/G) | Composite RGY status rolled up from all dimensions above. | 1 | Must | M | 7 | 56 | 4 | 32
F-113 | Module 3 - SRM | Monitor, Alerts & Reporting | Automatic Alerts (6W / 4W / 2W / Overdue) | Time-based alert cadence ahead of each milestone. | 1 | Must | L | 10 | 80 | 7 | 56
F-114 | Module 3 - SRM | Monitor, Alerts & Reporting | Escalation to Supervisors & Management | Escalate unresolved alerts up the chain. | 1 | Must | M | 6 | 48 | 4 | 32
F-115 | Module 3 - SRM | Monitor, Alerts & Reporting | Performance Dashboard | Supplier and part-level performance view. | 1 | Must | M | 8 | 64 | 5 | 40
F-116 | Module 3 - SRM | Monitor, Alerts & Reporting | SRM Reports | Auto-generated Status Tracking Report (PPT/PDF) circulated to stakeholders. | 1 | Must | M | 8 | 64 | 5 | 40
F-117 | Module 3 - SRM | Monitor, Alerts & Reporting | AI Chatbot & Forecasting | Query SRM status conversationally; forecast likely delays. | 3 | Must | L | 16 | 128 | 11 | 88
F-118 | Module 3 - SRM | AI-Powered Insights & Reports | Supplier Readiness Overview | Portfolio-level view of readiness across all suppliers/parts. | 1 | Must | M | 7 | 56 | 4 | 32
F-119 | Module 3 - SRM | AI-Powered Insights & Reports | Milestone Heatmap (Projects / Parts) | Visual heatmap of milestone health across the portfolio. | 3 | Could | L | 10 | 80 | 6 | 48
F-120 | Module 3 - SRM | AI-Powered Insights & Reports | Delay & Risk Prediction | AI-predicted likelihood of milestone delay. | 3 | Could | L | 16 | 128 | 11 | 88
F-121 | Module 3 - SRM | AI-Powered Insights & Reports | Supplier Performance Ranking | Ranked view of suppliers by readiness/risk/performance. | 3 | Could | L | 8 | 64 | 5 | 40
F-122 | Module 3 - SRM | AI-Powered Insights & Reports | Executive Dashboard & PowerPoint | Management-ready rollup, exportable to PPT. | 1 | Must | M | 8 | 64 | 5 | 40
F-123 | Module 3 - SRM | AI-Powered Insights & Reports | AI Chatbot for SRM Queries | Natural-language SRM query capability. | 1 | Must | L | 14 | 112 | 10 | 80
F-124 | Cross-Cutting Platform | Platform Services | Master Data Core | Project, Part, Supplier, Commodity/FX, Tooling, BOM, Buyer-Material Relationship, CBD tree — single governed source. | 1 | Must | L | 20 | 160 | 16 | 128
F-125 | Cross-Cutting Platform | Platform Services | Workflow / Approval Engine | Configurable, type-specific approval routing with unique workflow numbering. | 1 | Must | L | 20 | 160 | 16 | 128
F-126 | Cross-Cutting Platform | Platform Services | Escalation Engine | Time-based escalation trigger, admin-configurable ladder. | 1 | Must | M | 10 | 80 | 8 | 64
F-127 | Cross-Cutting Platform | Platform Services | Dashboards & Reports (platform-wide) | Material Cost, Investment, Benchmarking, Tooling/Readiness, SRM Status, AEKO Tracking, Operational. | 1 | Must | M | 12 | 96 | 7 | 56
F-128 | Cross-Cutting Platform | Platform Services | AI Assistant (platform-wide) | Text + graphical query, forecasting, auto-report generation across laptop/iPad/mobile. | 1 | Must | L | 28 | 224 | 20 | 160
F-129 | Cross-Cutting Platform | Platform Services | Security & Access Control | SSO/PKI auth, RBAC, VW Group Annexure A compliance (~90 clauses, 6 sections). | 1 | Must | L | 22 | 176 | 18 | 144
F-130 | Cross-Cutting Platform | Platform Services | In-App Task / Notification Centre | Dedicated “My Tasks” view, distinct from Approvals Inbox. | 1 | Must | M | 8 | 64 | 4 | 32
F-131 | Cross-Cutting Platform | Platform Services | Historical Data Pre-Fill | Bulk load of historical price/cost/SRM data prior to go-live. | 1 | Must | M | 8 | 64 | 5 | 40
F-132 | Cross-Cutting Platform | Platform Services | Dev / Test / Prod Environments | Three isolated environments with promotion pipeline. | 1 | Must | M | 8 | 64 | 6 | 48
F-133 | Cross-Cutting Platform | Platform Services | Training Materials & FAQ | User manual, video tutorial, FAQ prior to go-live. | 1 | Must | S | 5 | 40 | 5 | 40
F-134 | Cross-Cutting Platform | Platform Services | UAT Support & Stabilisation | 4-month go-live incl. UAT, 1-month post-go-live stabilisation. | 1 | Must | L | 20 | 160 | 18 | 144
F-135 | Module 1 - Procurement | Source & Nominate | Mass Data Upload Utility (CBD — 2 Formats) | Generic mass-upload utility supporting both SAVWIPL Cost Breakdown template formats, used across master and transactional data updates. | 1 | Must | L | 15 | 120 | 9 | 72
F-136 | Module 1 - Procurement | Commercial Management | Imported Parts Pricing (Group Company Block/Dummy Price → Actual SOP Price) | Pre-SOP: capture a dummy part number / block price for imported parts sourced from Group Companies. At SOP: replace with the actual part number and price. | 1 | Must | M | 6 | 48 | 3 | 24
F-137 | Module 1 - Procurement | Approve & Execute | EBON Annual PO Mass-Update Reminder (November) | Automated annual reminder, triggered every November, prompting Buyers to update EBON Purchase Orders wherever yearly price reductions apply. | 1 | Must | S | 3 | 24 | 3 | 24
F-138 | Module 1 - Procurement | Source & Nominate | Random Project Data Upload (Benchmarking) | Dedicated upload workflow for external / other-project data used purely for benchmarking comparisons, kept separate from the active project’s own master and transactional data. | 1 | Should | S | 4 | 32 | 2 | 16
F-139 | Module 2 - Technical Change | Change Initiation | MOD Sheet Auto-Population & Controlled Overwrite | System pre-fills the MOD Sheet format with current prices from the knowledge source; Buyer can overwrite with new prices via a controlled, logged action (no silent overwrite). | 2 | Must | M | 7 | 56 | 5 | 40
F-140 | Module 2 - Technical Change | Change Initiation | Restricted External / Outside-India User Access | Provision for outside-India colleagues to receive a restricted login limited strictly to the Technical Change Evaluation module, with no access to other modules. | 2 | Must | M | 6 | 48 | 5 | 40
F-141 | Module 3 - SRM | Part Assignment | Part Colour Code / Fakum Mapping to Base Part | Capture part numbers with colour code / Fakum variants against a base part number, where the variant is not already available in the base part record. | 1 | Must | S | 4 | 32 | 2 | 16
F-142 | Module 3 - SRM | Milestone Tracking | Milestone Amendment Approval with Strikethrough History | Any amendment to a first-entered milestone date must route through Supervisor / Commodity Lead approval; the prior value remains visible with strikethrough formatting on dashboards and reports. | 1 | Must | M | 6 | 48 | 4 | 32
F-143 | Cross-Cutting Platform | Platform Services | AI Model Abstraction Layer (Vendor AI vs SAVWIPL AI) | Architecture layer allowing the chatbot/analytics engine to run on either a vendor-hosted AI model or a SAVWIPL-provided AI model, matching the two commercial options requested in the RFQ. | 1 | Must | L | 20 | 160 | 16 | 128
F-144 | Cross-Cutting Platform | Platform Services | Operational Dashboard (Platform Health & Usage) | Monitoring dashboard covering system usage, workflow throughput, and platform health indicators — distinct from the business-facing dashboards. | 1 | Must | M | 8 | 64 | 5 | 40
F-145 | Cross-Cutting Platform | Platform Services | Multi-Device Responsive Access (Laptop / iPad / Mobile) | Platform-wide responsive access to all modules and dashboards (not only the AI chatbot) across official laptop, iPad, and mobile devices. | 1 | Must | L | 12 | 160 | 10 | 120
F-146 | Cross-Cutting Platform | Platform Services | Email Server Integration (SMTP / Exchange Setup) | Core integration with the customer’s email server enabling every reminder, alert, and approval-note communication across all three modules. | 1 | Must | M | 6 | 48 | 5 | 40
F-147 | Cross-Cutting Platform | Platform Services | OCR / Scanned Document Extraction (Optional) | Optional OCR layer to extract data from scanned (non-digital) PDFs for Technical Change document ingestion, if confirmed in scope during pre-bid clarification. | 3 | Could | L | 15 | 120 | 11 | 88
F-148 | Cross-Cutting Platform | Platform Services | Annual AI / Software Version Upgrade | Yearly upgrade of the AI model / software version at no additional cost, per the RFQ commercial requirement. | 3 | Must | M | 5 | 40 | 5 | 40
[9 empty] | 9872 | 793 | 6560

## Summary
Module | Total Features | RFQ Traceability | Scope Review Flags | Must | Should | Could | Phase 1 | Phase 2 | Phase 3 | Small | Medium | Large
Module 1 - Procurement | 40 | Not captured | 5 | 32 | 6 | 2 | 39 | 0 | 1 | 6 | 22 | 12
Procurement Orders | 4 | Not captured | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 2
Module 2 - Technical Change | 41 | Not captured | 0 | 28 | 11 | 2 | 0 | 39 | 2 | 6 | 26 | 9
Module 3 - SRM | 46 | Not captured | 0 | 33 | 10 | 3 | 42 | 0 | 4 | 7 | 23 | 16
Cross-Cutting Platform | 17 | Not captured | 0 | 16 | 0 | 1 | 15 | 0 | 2 | 1 | 8 | 8
Total | 148 | 0 | 9 | 113 | 27 | 8 | 100 | 39 | 9 | 20 | 81 | 47

## Legend
Column | Meaning
Feature ID | Unique sequential reference (F-001, F-002...)
Module | Platform module the feature belongs to (colour-coded, matching Summary sheet)
Stage | The workflow stage this feature sits in (per the three approved workflow visuals)
Feature | Short feature name, exactly as it appears in the Deep-Dive Feature Specification v0.2
What It Does | One-line functional description
Status | Confirmed FR = traceable to an original Functional Requirement (BRD v0.1). ★ Newly Surfaced = named in the workflow visuals but not in the original 50 FRs — needs a scope/priority decision
FR Ref | Functional Requirement number(s) this feature maps to, where applicable
Open Item Ref | Cross-reference to the Estimation Risk Register (#1–#11) in the BRD / Deep-Dive doc, where this feature carries an open question
Phase | 1 = Core Go-Live, 2 = Technical Change optional package, 3 = Advanced AI/Forecasting
Priority (MoSCoW) | Must / Should / Could. Confirmed FR items default to Must; newly-surfaced items are Should unless they are pure AI/analytics add-ons (Could). Review before finalising.
Complexity (S/M/L) | Small / Medium / Large — a relative sizing input for the estimator, assigned heuristically from feature type (data tree, AI/extraction, and mass-upload features trend Large; simple CRUD/master fields trend Small). Re-validate for anything estimation-critical.
Effort Estimate (Person-Days)
Architect Notes | Free-text field for architects to record assumptions, dependencies, or design notes affecting the effort estimate.
Note: Priority and Complexity are heuristic starting points generated for this inventory, not confirmed estimates — validate with the delivery team, especially for every ★ Newly Surfaced and every row carrying an Open Item Ref.

## Review Summary
SAVWIPL AIS – Feature Inventory & Effort Review
Review of procurement digitalisation, technical change evaluation, SRM and cross-cutting platform work. Estimates are normalized to 8-hour person-days.
Inventory Quality | Value | Finding | Action
Rows reviewed | 150 | 148 numbered features + 2 unnumbered rows | Retain one consistent WBS numbering scheme
Original manual effort (normalized PD) | 1234 | Computed from 9,872 hours | Use hours as current source of truth
Original Claude effort (normalized PD) | 820 | Computed from 6,560 hours | Current saving assumption is aggressive
Current implied Claude saving | 33.55% | Across listed feature hours | Revalidate by work type and SDLC role
Recommended feature manual effort (most likely PD) | 1965 | Feature-level re-baseline | Still excludes de-duplicated project-level gaps
Recommended feature Claude effort (most likely PD) | 1598 | Enterprise-lifecycle-aware AI benefit | Use as planning baseline, not commitment
Coverage gap work packages | 63 | Missing, partial or clarification items | Add/decompose before commercial submission
Summary formula issue | 2 | Original Summary has broken C/D formulas | Add traceability columns or use Review Summary
Module | Current Manual PD | Current Claude PD | Reviewed Manual PD | Reviewed Claude PD
Module 1 - Procurement | 340 | 213 | 565 | 446
Procurement Orders | 34 | 23 | 41 | 31
Module 2 - Technical Change | 294 | 197 | 455 | 368
Module 3 - SRM | 301 | 185 | 410 | 323
Cross-Cutting Platform | 235 | 180 | 494 | 430
Unassigned | 30 | 22 | 0 | 0
Assessment | Count | Current Manual PD | Reviewed Manual PD
Underestimated | 35 | 394 | 759
Broadly reasonable | 86 | 499 | 633
Scope confirmation required | 9 | 62 | 74
Shared-enabler boundary required | 17 | 235 | 494
Potential overlap / overestimate | 1 | 14 | 5
Merge / remove from total | 2 | 30 | 0
Critical Review Findings |  |  |  |  | Gap Category | Items | Manual Low | Manual Most Likely | Claude Most Likely
# | Issue | Evidence | Recommended Action |  | Discovery & Governance | 10 | 249 | 335 | 271
1 | Duplicate unnumbered rows | Authentication & Authorization overlaps F-129; Notification Module overlaps F-026/F-126/F-130/F-146. | Remove from totals or retain only as non-estimated epic headings. |  | Platform Administration | 9 | 118 | 171 | 137
2 | Mixed WBS levels | The inventory mixes epics, shared engines, integrations, screens, business rules and delivery activities. | Add WBS Level, Parent Feature and Estimate Boundary columns. |  | Data & Integration | 8 | 141 | 196 | 171
3 | Broken traceability | Legend describes Status, FR Ref and Open Item Ref, but those columns are absent; Summary formulas consequently fail. | Add an RFQ-to-feature traceability matrix before bid submission. |  | Procurement Rules | 5 | 41 | 61 | 45
4 | Scope expansion risk | F-007 to F-011 and F-037 to F-040 are not clearly explicit in the RFQ baseline. | Confirm as in-scope, optional or future phase. |  | Technical Change Rules | 4 | 31 | 46 | 37
5 | Shared-platform double count | F-124 to F-130 and F-143 to F-146 can overlap with module-level tasks. | Estimate foundation once; module rows should cover configuration/incremental effort. |  | SRM Rules | 4 | 31 | 46 | 35
6 | AI duplication | F-117 and F-123 overlap; F-128 also overlaps all module chatbots. | Use one shared AI platform plus module-specific intents, schemas and test packs. |  | AI Governance & MLOps | 7 | 139 | 193 | 166
7 | Estimate conversion errors | Rows 2–3 contain hours without days; F-145 shows 12 days/160 hours and 10 AI days/120 hours. | Standardize on 8-hour days and formula-driven hour/day conversion. |  | Quality & Non-Functional | 7 | 182 | 245 | 211
8 | Full-project work absent | BRD, UX, architecture, QA, performance, security, migration, DevOps, training delivery, cutover and support setup are not consistently estimated. | Add the Coverage Gaps work packages and re-baseline. |  | DevOps & Operations | 4 | 71 | 100 | 88
9 | AI saving assumption | Current hours imply 33.6% saving, including work that is not strongly AI-compressible. | Apply AI factors by task type; validate with historical delivery data. |  | Training & Go-Live | 5 | 78 | 110 | 101
10 | Four-month timeline | The current list represents 100 Phase-1 features before missing delivery tasks are considered. | Deliver a prioritized MVP and run parallel workstreams; do not promise all advanced AI and integrations in one release.

## Feature Estimate Review
Source Row | Feature ID | Module | Stage | Feature | Phase | Priority | Complexity | Current Manual PD (Normalized from Hours) | Current Claude AI PD (Normalized from Hours) | Estimate Category | Assessment | Recommended Manual PD - Low | Recommended Manual PD - Most Likely | Recommended Manual PD - High | Recommended Claude AI PD - Most Likely | Confidence | Review Rationale
2 | UNNUMBERED | Unassigned | Unassigned | Authentication & Authorization | 1 |  | S | 10 | 7 | Duplicate / unnumbered | Merge / remove from total | 0 | 0 | 0 | 0 | High | Unnumbered and overlaps with cross-cutting Security/Access and Notification/Task Centre features; retain only as epic headings.
3 | UNNUMBERED | Unassigned | Unassigned | Notification Module | 1 |  | L | 20 | 15 | Duplicate / unnumbered | Merge / remove from total | 0 | 0 | 0 | 0 | High | Unnumbered and overlaps with cross-cutting Security/Access and Notification/Task Centre features; retain only as epic headings.
4 | F-001 | Module 1 - Procurement | Define & Plan | Create Project | 1 | Must | M | 5 | 3 | CRUD / configuration | Broadly reasonable | 4 | 6 | 7 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
5 | F-002 | Module 1 - Procurement | Define & Plan | Upload BOM & Part List | 1 | Must | L | 12 | 7 | Data ingestion / migration | Underestimated | 15 | 19 | 25 | 15 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
6 | F-003 | Module 1 - Procurement | Define & Plan | Maintain Master Data (Project, Part, Supplier, Commodity, FX) | 1 | Must | L | 15 | 8 | Complex data / calculation | Broadly reasonable | 18 | 22 | 30 | 17 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
7 | F-004 | Module 1 - Procurement | Define & Plan | Define Commodity & Exchange Rate | 1 | Must | M | 6 | 3 | Complex data / calculation | Underestimated | 7 | 9 | 12 | 7 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
8 | F-005 | Module 1 - Procurement | Define & Plan | Define Milestones & Targets | 1 | Must | L | 10 | 7 | CRUD / configuration | Broadly reasonable | 9 | 11 | 14 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
9 | F-006 | Module 1 - Procurement | Source & Nominate | Import Sourcing Report (EBON+) | 1 | Must | L | 18 | 11 | External integration | Underestimated | 28 | 36 | 48 | 28 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
10 | F-007 | Module 1 - Procurement | Source & Nominate | RFQ Management | 1 | Should | M | 7 | 5 | Scope clarification | Scope confirmation required | 7 | 8 | 11 | 6 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
11 | F-008 | Module 1 - Procurement | Source & Nominate | Supplier Quotations | 1 | Should | M | 6 | 4 | Scope clarification | Scope confirmation required | 6 | 7 | 10 | 5 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
12 | F-009 | Module 1 - Procurement | Source & Nominate | Supplier Comparison | 1 | Should | S | 4 | 2 | Scope clarification | Scope confirmation required | 4 | 5 | 6 | 4 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
13 | F-010 | Module 1 - Procurement | Source & Nominate | Supplier Nomination | 1 | Must | M | 5 | 3 | Scope clarification | Scope confirmation required | 5 | 6 | 8 | 5 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
14 | F-011 | Module 1 - Procurement | Source & Nominate | Commercial Negotiation | 1 | Must | M | 6 | 4 | Scope clarification | Scope confirmation required | 6 | 7 | 10 | 5 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
15 | F-012 | Module 1 - Procurement | Commercial Management | Cost Breakdown (CBD) | 1 | Must | L | 18 | 13 | Complex data / calculation | Underestimated | 32 | 42 | 56 | 33 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
16 | F-013 | Module 1 - Procurement | Commercial Management | Price Tracking & History | 1 | Must | M | 7 | 4 | Complex data / calculation | Broadly reasonable | 8 | 10 | 14 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
17 | F-014 | Module 1 - Procurement | Commercial Management | Investment Cost | 1 | Must | M | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
18 | F-015 | Module 1 - Procurement | Commercial Management | Tooling Cost | 1 | Must | M | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
19 | F-016 | Module 1 - Procurement | Commercial Management | Commodity Prices | 1 | Must | M | 6 | 3 | Complex data / calculation | Underestimated | 7 | 9 | 12 | 7 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
20 | F-017 | Module 1 - Procurement | Commercial Management | Forex Impact | 1 | Must | M | 6 | 3 | Complex data / calculation | Underestimated | 7 | 9 | 12 | 7 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
21 | F-018 | Module 1 - Procurement | Commercial Management | Target Cost | 1 | Must | M | 5 | 3 | Complex data / calculation | Underestimated | 6 | 8 | 10 | 6 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
22 | F-019 | Module 1 - Procurement | Commercial Management | Business Share Allocation | 1 | Should | M | 5 | 3 | Complex data / calculation | Underestimated | 6 | 8 | 10 | 6 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
23 | F-020 | Module 1 - Procurement | Commercial Management | BOM Cost Rollup | 1 | Must | L | 12 | 8 | Complex data / calculation | Underestimated | 18 | 24 | 32 | 19 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
24 | F-021 | Module 1 - Procurement | Approve & Execute | Commercial Approval | 1 | Must | M | 6 | 4 | Workflow / approval | Broadly reasonable | 5 | 7 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
25 | F-022 | Module 1 - Procurement | Approve & Execute | Commodity Approval | 1 | Must | M | 5 | 3 | Workflow / approval | Broadly reasonable | 4 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
26 | F-023 | Module 1 - Procurement | Approve & Execute | Management Approval | 1 | Must | M | 5 | 3 | Workflow / approval | Broadly reasonable | 4 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
27 | F-024 | Module 1 - Procurement | Approve & Execute | PO Creation | 1 | Must | L | 10 | 7 | External integration | Underestimated | 20 | 30 | 45 | 26 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
28 | F-025 | Module 1 - Procurement | Approve & Execute | PO Tracking | 1 | Should | M | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
29 | F-026 | Module 1 - Procurement | Approve & Execute | Notifications & Alerts | 1 | Must | S | 4 | 2 | Workflow / approval | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
30 | F-027 | Module 1 - Procurement | Approve & Execute | Escalations | 1 | Must | M | 6 | 4 | Workflow / approval | Broadly reasonable | 5 | 7 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
31 | F-028 | Module 1 - Procurement | Approve & Execute | Audit Trail | 1 | Must | S | 4 | 2 | Standard functional feature | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
32 | F-029 | Module 1 - Procurement | Analyse & Optimise | Material Cost Dashboard | 1 | Must | M | 8 | 5 | Dashboard / reporting | Broadly reasonable | 9 | 11 | 14 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
33 | F-030 | Module 1 - Procurement | Analyse & Optimise | Investment Dashboard | 1 | Must | M | 7 | 4 | Dashboard / reporting | Broadly reasonable | 8 | 10 | 13 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
34 | F-031 | Module 1 - Procurement | Analyse & Optimise | Benchmarking Dashboard | 1 | Must | S | 5 | 3 | Dashboard / reporting | Broadly reasonable | 6 | 7 | 9 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
35 | F-032 | Module 1 - Procurement | Analyse & Optimise | AI Chatbot (Q&A) | 1 | Must | L | 25 | 18 | AI / ML / Intelligent automation | Underestimated | 40 | 50 | 70 | 41 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
36 | F-033 | Module 1 - Procurement | Analyse & Optimise | Commodity Forecasting | 3 | Must | L | 20 | 14 | AI / ML / Intelligent automation | Underestimated | 28 | 36 | 48 | 30 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
37 | F-034 | Module 1 - Procurement | Analyse & Optimise | Cost Saving Opportunities | 1 | Could | L | 18 | 13 | AI / ML / Intelligent automation | Underestimated | 25 | 32 | 43 | 26 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
38 | F-035 | Module 1 - Procurement | Analyse & Optimise | Automated Reports (PPT/PDF/Excel) | 1 | Must | L | 12 | 7 | Dashboard / reporting | Underestimated | 18 | 24 | 32 | 18 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
39 | F-036 | Module 1 - Procurement | Analyse & Optimise | Executive Summary | 1 | Could | M | 6 | 4 | Dashboard / reporting | Broadly reasonable | 7 | 8 | 11 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
40 | F-037 | Procurement Orders | General | Component-Level Hierarchy Mapping | 1 | Must | L | 14 | 10 | Scope clarification | Scope confirmation required | 14 | 17 | 22 | 13 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
41 | F-038 | Procurement Orders | General | Requirement-Raising Workflow | 1 | Must | M | 6 | 4 | Scope clarification | Scope confirmation required | 6 | 7 | 10 | 5 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
42 | F-039 | Procurement Orders | General | Fulfilment Status Tracker | 1 | Must | M | 6 | 4 | Scope clarification | Scope confirmation required | 6 | 7 | 10 | 5 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
43 | F-040 | Procurement Orders | General | Cross-Module Linking | 1 | Must | L | 8 | 5 | Scope clarification | Scope confirmation required | 8 | 10 | 13 | 8 | Low | Not clearly stated in the RFQ baseline; include only after customer confirmation or treat as optional enhancement.
44 | F-041 | Module 2 - Technical Change | Change Initiation | Create Change (AEKO / AWE / AeA / Running Change / MY Change / Supplier Proposal) | 2 | Should | M | 7 | 5 | CRUD / configuration | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
45 | F-042 | Module 2 - Technical Change | Change Initiation | Upload Documents (PDF / Excel / Drawings) | 2 | Must | M | 5 | 3 | Data ingestion / migration | Underestimated | 6 | 8 | 10 | 6 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
46 | F-043 | Module 2 - Technical Change | Change Initiation | AI Document Processing & Auto-Extraction | 2 | Must | L | 22 | 15 | AI / ML / Intelligent automation | Underestimated | 34 | 45 | 60 | 37 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
47 | F-044 | Module 2 - Technical Change | Change Initiation | System Generates Change ID & Workflow No. | 2 | Must | M | 3 | 2 | Workflow / approval | Broadly reasonable | 3 | 4 | 5 | 3 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
48 | F-045 | Module 2 - Technical Change | Validation & Triage | Automatic Data Validation | 2 | Should | S | 4 | 2 | Standard functional feature | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
49 | F-046 | Module 2 - Technical Change | Validation & Triage | Check Project, Part, Supplier, BOM, Price, Revision | 2 | Must | S | 4 | 2 | Standard functional feature | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
50 | F-047 | Module 2 - Technical Change | Validation & Triage | Assign Buyer, SRM Engineer, Engineering Owner, Approver | 2 | Must | S | 4 | 2 | Workflow / approval | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
51 | F-048 | Module 2 - Technical Change | Validation & Triage | Return for Correction if Validation Fails | 2 | Should | M | 4 | 3 | Standard functional feature | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
52 | F-049 | Module 2 - Technical Change | Impact Analysis | Commercial Impact | 2 | Must | L | 10 | 7 | Standard functional feature | Broadly reasonable | 10 | 12 | 16 | 9 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
53 | F-050 | Module 2 - Technical Change | Impact Analysis | Technical Impact | 2 | Should | M | 6 | 4 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
54 | F-051 | Module 2 - Technical Change | Impact Analysis | Supply Chain Impact | 2 | Should | M | 6 | 4 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
55 | F-052 | Module 2 - Technical Change | Impact Analysis | Production Impact | 2 | Should | M | 6 | 4 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
56 | F-053 | Module 2 - Technical Change | Impact Analysis | Cost Analysis & Savings / Increase | 2 | Must | M | 7 | 5 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
57 | F-054 | Module 2 - Technical Change | Impact Analysis | AI Insights: Similar Changes, Risk Prediction | 3 | Could | L | 20 | 14 | AI / ML / Intelligent automation | Underestimated | 28 | 36 | 48 | 30 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
58 | F-055 | Module 2 - Technical Change | Supplier Evaluation | Send Change Package to Supplier | 2 | Must | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
59 | F-056 | Module 2 - Technical Change | Supplier Evaluation | Supplier Submits Offer, Timeline, Investment, Tooling, Capacity | 2 | Must | M | 7 | 5 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
60 | F-057 | Module 2 - Technical Change | Supplier Evaluation | Upload Supporting Documents | 2 | Must | M | 4 | 2 | Data ingestion / migration | Underestimated | 5 | 6 | 8 | 5 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
61 | F-058 | Module 2 - Technical Change | Supplier Evaluation | Buyer Review & Clarification Loop | 2 | Should | M | 6 | 4 | Workflow / approval | Broadly reasonable | 5 | 7 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
62 | F-059 | Module 2 - Technical Change | Supplier Evaluation | Final Offer Locked | 2 | Must | L | 6 | 4 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
63 | F-060 | Module 2 - Technical Change | Approval Workflow | Engineering Approval | 2 | Must | M | 5 | 3 | Workflow / approval | Broadly reasonable | 4 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
64 | F-061 | Module 2 - Technical Change | Approval Workflow | Quality Approval | 2 | Must | M | 5 | 3 | Workflow / approval | Broadly reasonable | 4 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
65 | F-062 | Module 2 - Technical Change | Approval Workflow | SRM Approval | 2 | Must | L | 6 | 4 | Workflow / approval | Broadly reasonable | 5 | 7 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
66 | F-063 | Module 2 - Technical Change | Approval Workflow | Finance Approval | 2 | Must | M | 5 | 3 | Workflow / approval | Broadly reasonable | 4 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
67 | F-064 | Module 2 - Technical Change | Approval Workflow | Commodity Approval | 2 | Must | M | 5 | 3 | Workflow / approval | Broadly reasonable | 4 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
68 | F-065 | Module 2 - Technical Change | Approval Workflow | Management Approval | 2 | Must | M | 5 | 3 | Workflow / approval | Broadly reasonable | 4 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
69 | F-066 | Module 2 - Technical Change | Approval Workflow | Digital Signatures, Comments & Version Control | 2 | Should | L | 12 | 10 | Workflow / approval | Underestimated | 18 | 22 | 30 | 18 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
70 | F-067 | Module 2 - Technical Change | Implementation & Control | ERP / Price Update | 2 | Must | L | 12 | 8 | External integration | Underestimated | 22 | 30 | 45 | 26 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
71 | F-068 | Module 2 - Technical Change | Implementation & Control | Supplier Notification | 2 | Must | S | 3 | 2 | Workflow / approval | Broadly reasonable | 3 | 4 | 5 | 3 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
72 | F-069 | Module 2 - Technical Change | Implementation & Control | Drawing Release | 2 | Should | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
73 | F-070 | Module 2 - Technical Change | Implementation & Control | Tool Order | 2 | Should | M | 6 | 4 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
74 | F-071 | Module 2 - Technical Change | Implementation & Control | BOM / PO Update | 2 | Must | M | 7 | 5 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
75 | F-072 | Module 2 - Technical Change | Implementation & Control | Plant / Quality / Production Notification | 2 | Should | S | 3 | 2 | Workflow / approval | Broadly reasonable | 3 | 4 | 5 | 3 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
76 | F-073 | Module 2 - Technical Change | Implementation & Control | Monitor & Track Implementation | 2 | Must | M | 6 | 4 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
77 | F-074 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Change Dashboard (Open / Pending / Approved) | 2 | Must | M | 7 | 4 | Dashboard / reporting | Broadly reasonable | 8 | 10 | 13 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
78 | F-075 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | AI Chatbot (Queries, Status, Cost Impact) | 2 | Must | L | 16 | 11 | AI / ML / Intelligent automation | Underestimated | 24 | 32 | 44 | 26 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
79 | F-076 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Reports & PPT (Excel / PowerPoint / PDF) | 2 | Must | M | 8 | 5 | External integration | Underestimated | 12 | 16 | 22 | 14 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
80 | F-077 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Change History & Audit Trail | 2 | Must | S | 4 | 2 | Standard functional feature | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
81 | F-078 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Cost Impact & Savings Analysis | 2 | Must | M | 7 | 5 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
82 | F-079 | Module 2 - Technical Change | Monitoring, Reporting & AI Insights | Risk Forecasting (Delay, Cost, Supplier Risk) | 3 | Could | L | 18 | 13 | AI / ML / Intelligent automation | Underestimated | 28 | 36 | 50 | 30 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
83 | F-080 | Module 3 - SRM | Part Assignment | Create SRM Project | 1 | Must | M | 5 | 3 | CRUD / configuration | Broadly reasonable | 4 | 6 | 7 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
84 | F-081 | Module 3 - SRM | Part Assignment | Import Parts & BOM | 1 | Must | M | 7 | 4 | Data ingestion / migration | Underestimated | 9 | 11 | 15 | 9 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
85 | F-082 | Module 3 - SRM | Part Assignment | Import Supplier List | 1 | Must | M | 6 | 4 | Data ingestion / migration | Underestimated | 8 | 9 | 13 | 7 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
86 | F-083 | Module 3 - SRM | Part Assignment | Assign KTM Expert | 1 | Must | S | 3 | 2 | Workflow / approval | Broadly reasonable | 3 | 4 | 5 | 3 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
87 | F-084 | Module 3 - SRM | Part Assignment | Assign QE, Buyer, SRM Engineer, Logistics, Tool Owner | 1 | Must | S | 4 | 2 | Workflow / approval | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
88 | F-085 | Module 3 - SRM | Part Assignment | Define Milestones | 1 | Must | L | 9 | 6 | CRUD / configuration | Underestimated | 14 | 18 | 25 | 14 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
89 | F-086 | Module 3 - SRM | Part Assignment | Start Monitoring | 1 | Must | S | 3 | 2 | CRUD / configuration | Broadly reasonable | 3 | 3 | 4 | 2 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
90 | F-087 | Module 3 - SRM | Supplier Onboarding | Supplier Master Data | 1 | Must | S | 4 | 2 | CRUD / configuration | Broadly reasonable | 4 | 4 | 6 | 3 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
91 | F-088 | Module 3 - SRM | Supplier Onboarding | Plant, Contacts, Tool Shop | 1 | Should | M | 5 | 3 | CRUD / configuration | Broadly reasonable | 4 | 6 | 7 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
92 | F-089 | Module 3 - SRM | Supplier Onboarding | Tool Maker & Cavities | 1 | Must | M | 4 | 2 | CRUD / configuration | Broadly reasonable | 4 | 4 | 6 | 3 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
93 | F-090 | Module 3 - SRM | Supplier Onboarding | Capacity, Location, Certifications | 1 | Should | M | 5 | 3 | CRUD / configuration | Broadly reasonable | 4 | 6 | 7 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
94 | F-091 | Module 3 - SRM | Supplier Onboarding | Commodity, Business Share | 1 | Should | M | 4 | 2 | Complex data / calculation | Underestimated | 5 | 6 | 8 | 5 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
95 | F-092 | Module 3 - SRM | Supplier Onboarding | Risk Rating & Performance | 1 | Should | L | 9 | 6 | Standard functional feature | Broadly reasonable | 9 | 11 | 14 | 9 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
96 | F-093 | Module 3 - SRM | Tool Readiness | Tool Number, Type, Location | 1 | Must | S | 3 | 2 | CRUD / configuration | Broadly reasonable | 3 | 3 | 4 | 2 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
97 | F-094 | Module 3 - SRM | Tool Readiness | Tool Maker & Cavities | 1 | Must | M | 4 | 2 | CRUD / configuration | Broadly reasonable | 4 | 4 | 6 | 3 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
98 | F-095 | Module 3 - SRM | Tool Readiness | Tool Kickoff | 1 | Must | L | 6 | 4 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
99 | F-096 | Module 3 - SRM | Tool Readiness | Tool Trial | 1 | Must | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
100 | F-097 | Module 3 - SRM | Tool Readiness | Tool Investment & Completion % | 1 | Must | M | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
101 | F-098 | Module 3 - SRM | Tool Readiness | Tool Trial & Shipment Status | 1 | Must | L | 7 | 5 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
102 | F-099 | Module 3 - SRM | Tool Readiness | First Parts | 1 | Must | L | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
103 | F-100 | Module 3 - SRM | Tool Readiness | Tool Photos & Maintenance | 1 | Must | S | 4 | 2 | Standard functional feature | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
104 | F-101 | Module 3 - SRM | Milestone Tracking | B Release | 1 | Must | L | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
105 | F-102 | Module 3 - SRM | Milestone Tracking | P-Frei / B-Frei | 1 | Must | L | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
106 | F-103 | Module 3 - SRM | Milestone Tracking | VFF → PVS → 0-Series | 1 | Must | L | 8 | 5 | Standard functional feature | Broadly reasonable | 8 | 10 | 13 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
107 | F-104 | Module 3 - SRM | Milestone Tracking | PPAP → SOP Readiness → SOP | 1 | Must | L | 8 | 5 | Standard functional feature | Broadly reasonable | 8 | 10 | 13 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
108 | F-105 | Module 3 - SRM | Readiness Assessment | Engineering | 1 | Should | L | 6 | 3 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
109 | F-106 | Module 3 - SRM | Readiness Assessment | Quality | 1 | Should | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
110 | F-107 | Module 3 - SRM | Readiness Assessment | Tooling | 1 | Must | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
111 | F-108 | Module 3 - SRM | Readiness Assessment | Capacity | 1 | Should | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
112 | F-109 | Module 3 - SRM | Readiness Assessment | Material | 1 | Should | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
113 | F-110 | Module 3 - SRM | Readiness Assessment | Logistics | 1 | Should | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
114 | F-111 | Module 3 - SRM | Readiness Assessment | Production | 1 | Should | M | 5 | 3 | Standard functional feature | Broadly reasonable | 5 | 6 | 8 | 5 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
115 | F-112 | Module 3 - SRM | Readiness Assessment | Overall Readiness Score (R/Y/G) | 1 | Must | M | 7 | 4 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
116 | F-113 | Module 3 - SRM | Monitor, Alerts & Reporting | Automatic Alerts (6W / 4W / 2W / Overdue) | 1 | Must | L | 10 | 7 | Standard functional feature | Underestimated | 14 | 18 | 24 | 14 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
117 | F-114 | Module 3 - SRM | Monitor, Alerts & Reporting | Escalation to Supervisors & Management | 1 | Must | M | 6 | 4 | Workflow / approval | Broadly reasonable | 5 | 7 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
118 | F-115 | Module 3 - SRM | Monitor, Alerts & Reporting | Performance Dashboard | 1 | Must | M | 8 | 5 | Dashboard / reporting | Broadly reasonable | 9 | 11 | 14 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
119 | F-116 | Module 3 - SRM | Monitor, Alerts & Reporting | SRM Reports | 1 | Must | M | 8 | 5 | Dashboard / reporting | Broadly reasonable | 9 | 11 | 14 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
120 | F-117 | Module 3 - SRM | Monitor, Alerts & Reporting | AI Chatbot & Forecasting | 3 | Must | L | 16 | 11 | AI / ML / Intelligent automation | Underestimated | 26 | 34 | 48 | 29 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
121 | F-118 | Module 3 - SRM | AI-Powered Insights & Reports | Supplier Readiness Overview | 1 | Must | M | 7 | 4 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
122 | F-119 | Module 3 - SRM | AI-Powered Insights & Reports | Milestone Heatmap (Projects / Parts) | 3 | Could | L | 10 | 6 | Dashboard / reporting | Broadly reasonable | 12 | 14 | 18 | 10 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
123 | F-120 | Module 3 - SRM | AI-Powered Insights & Reports | Delay & Risk Prediction | 3 | Could | L | 16 | 11 | AI / ML / Intelligent automation | Underestimated | 22 | 29 | 38 | 24 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
124 | F-121 | Module 3 - SRM | AI-Powered Insights & Reports | Supplier Performance Ranking | 3 | Could | L | 8 | 5 | Dashboard / reporting | Broadly reasonable | 9 | 11 | 14 | 8 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
125 | F-122 | Module 3 - SRM | AI-Powered Insights & Reports | Executive Dashboard & PowerPoint | 1 | Must | M | 8 | 5 | External integration | Underestimated | 12 | 16 | 22 | 14 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
126 | F-123 | Module 3 - SRM | AI-Powered Insights & Reports | AI Chatbot for SRM Queries | 1 | Must | L | 14 | 10 | AI / ML / Intelligent automation | Potential overlap / overestimate | 3 | 5 | 8 | 4 | High | Overlaps with F-117 and F-128. Treat as SRM-specific configuration on the shared AI assistant, not a second chatbot build.
127 | F-124 | Cross-Cutting Platform | Platform Services | Master Data Core | 1 | Must | L | 20 | 16 | Platform / delivery | Shared-enabler boundary required | 28 | 35 | 48 | 29 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
128 | F-125 | Cross-Cutting Platform | Platform Services | Workflow / Approval Engine | 1 | Must | L | 20 | 16 | Workflow / approval | Shared-enabler boundary required | 34 | 45 | 60 | 38 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
129 | F-126 | Cross-Cutting Platform | Platform Services | Escalation Engine | 1 | Must | M | 10 | 8 | Workflow / approval | Shared-enabler boundary required | 9 | 12 | 16 | 10 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
130 | F-127 | Cross-Cutting Platform | Platform Services | Dashboards & Reports (platform-wide) | 1 | Must | M | 12 | 7 | Dashboard / reporting | Shared-enabler boundary required | 14 | 18 | 26 | 14 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
131 | F-128 | Cross-Cutting Platform | Platform Services | AI Assistant (platform-wide) | 1 | Must | L | 28 | 20 | AI / ML / Intelligent automation | Shared-enabler boundary required | 42 | 55 | 75 | 46 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
132 | F-129 | Cross-Cutting Platform | Platform Services | Security & Access Control | 1 | Must | L | 22 | 18 | Platform / delivery | Shared-enabler boundary required | 38 | 50 | 70 | 45 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
133 | F-130 | Cross-Cutting Platform | Platform Services | In-App Task / Notification Centre | 1 | Must | M | 8 | 4 | Workflow / approval | Shared-enabler boundary required | 12 | 16 | 22 | 12 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
134 | F-131 | Cross-Cutting Platform | Platform Services | Historical Data Pre-Fill | 1 | Must | M | 8 | 5 | Data ingestion / migration | Shared-enabler boundary required | 24 | 35 | 55 | 31 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
135 | F-132 | Cross-Cutting Platform | Platform Services | Dev / Test / Prod Environments | 1 | Must | M | 8 | 6 | Platform / delivery | Shared-enabler boundary required | 15 | 20 | 30 | 18 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
136 | F-133 | Cross-Cutting Platform | Platform Services | Training Materials & FAQ | 1 | Must | S | 5 | 5 | Platform / delivery | Shared-enabler boundary required | 7 | 9 | 12 | 8 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
137 | F-134 | Cross-Cutting Platform | Platform Services | UAT Support & Stabilisation | 1 | Must | L | 20 | 18 | Platform / delivery | Shared-enabler boundary required | 40 | 60 | 90 | 57 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
138 | F-135 | Module 1 - Procurement | Source & Nominate | Mass Data Upload Utility (CBD — 2 Formats) | 1 | Must | L | 15 | 9 | Data ingestion / migration | Underestimated | 22 | 30 | 42 | 23 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
139 | F-136 | Module 1 - Procurement | Commercial Management | Imported Parts Pricing (Group Company Block/Dummy Price → Actual SOP Price) | 1 | Must | M | 6 | 3 | Data ingestion / migration | Underestimated | 8 | 9 | 13 | 7 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
140 | F-137 | Module 1 - Procurement | Approve & Execute | EBON Annual PO Mass-Update Reminder (November) | 1 | Must | S | 3 | 3 | External integration | Underestimated | 4 | 6 | 8 | 5 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
141 | F-138 | Module 1 - Procurement | Source & Nominate | Random Project Data Upload (Benchmarking) | 1 | Should | S | 4 | 2 | Data ingestion / migration | Underestimated | 5 | 6 | 8 | 5 | Medium | Current estimate does not fully reflect enterprise validation, error handling, integration, security, audit and test effort.
142 | F-139 | Module 2 - Technical Change | Change Initiation | MOD Sheet Auto-Population & Controlled Overwrite | 2 | Must | M | 7 | 5 | Standard functional feature | Broadly reasonable | 7 | 9 | 11 | 7 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
143 | F-140 | Module 2 - Technical Change | Change Initiation | Restricted External / Outside-India User Access | 2 | Must | M | 6 | 5 | Standard functional feature | Broadly reasonable | 6 | 8 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
144 | F-141 | Module 3 - SRM | Part Assignment | Part Colour Code / Fakum Mapping to Base Part | 1 | Must | S | 4 | 2 | Standard functional feature | Broadly reasonable | 4 | 5 | 6 | 4 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
145 | F-142 | Module 3 - SRM | Milestone Tracking | Milestone Amendment Approval with Strikethrough History | 1 | Must | M | 6 | 4 | Workflow / approval | Broadly reasonable | 5 | 7 | 10 | 6 | Medium | Reasonable as a build estimate, subject to confirmed acceptance criteria, data volumes and shared-platform assumptions.
146 | F-143 | Cross-Cutting Platform | Platform Services | AI Model Abstraction Layer (Vendor AI vs SAVWIPL AI) | 1 | Must | L | 20 | 16 | AI / ML / Intelligent automation | Shared-enabler boundary required | 26 | 35 | 50 | 31 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
147 | F-144 | Cross-Cutting Platform | Platform Services | Operational Dashboard (Platform Health & Usage) | 1 | Must | M | 8 | 5 | Dashboard / reporting | Shared-enabler boundary required | 12 | 16 | 24 | 14 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
148 | F-145 | Cross-Cutting Platform | Platform Services | Multi-Device Responsive Access (Laptop / iPad / Mobile) | 1 | Must | L | 20 | 15 | Platform / delivery | Shared-enabler boundary required | 22 | 28 | 40 | 25 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
149 | F-146 | Cross-Cutting Platform | Platform Services | Email Server Integration (SMTP / Exchange Setup) | 1 | Must | M | 6 | 5 | External integration | Shared-enabler boundary required | 10 | 15 | 22 | 13 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
150 | F-147 | Cross-Cutting Platform | Platform Services | OCR / Scanned Document Extraction (Optional) | 3 | Could | L | 15 | 11 | AI / ML / Intelligent automation | Shared-enabler boundary required | 25 | 35 | 50 | 29 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.
151 | F-148 | Cross-Cutting Platform | Platform Services | Annual AI / Software Version Upgrade | 3 | Must | M | 5 | 5 | AI / ML / Intelligent automation | Shared-enabler boundary required | 8 | 10 | 15 | 10 | Medium | Valid shared platform work, but module rows must be estimated as incremental configuration to avoid double counting.

## Coverage Gaps
Gap ID | Category | Work Package / Missing Task | Coverage Status | Source / Requirement Reference | Manual PD - Low | Manual PD - Most Likely | Manual PD - High | Claude AI PD - Most Likely | Estimate Handling | Review Note
G-001 | Discovery & Governance | BRD preparation, workshops and customer approval | Requirement | RFQ Requirements + Statistics rows 47-49 | 30 | 40 | 55 | 32 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-002 | Discovery & Governance | Requirement traceability matrix (RFQ row-to-feature-to-test mapping) | Requirement | Needed for bid and scope control | 8 | 10 | 14 | 7 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-003 | Discovery & Governance | Detailed functional design, user stories and acceptance criteria | Design | All modules | 25 | 35 | 50 | 25 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-004 | Discovery & Governance | UX/UI research, wireframes, design system and responsive prototypes | Design | Laptop/iPad/mobile scope | 32 | 45 | 60 | 32 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-005 | Discovery & Governance | Solution architecture and deployment topology | Design | Technical Solution Document architecture dependency | 18 | 25 | 35 | 20 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-006 | Discovery & Governance | Data architecture, logical/physical model, data dictionary and governance | Design | Central governed repository | 22 | 30 | 45 | 24 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-007 | Discovery & Governance | Integration assessment, interface contracts and API/file specifications | Design | EBON/SAP/email/market data | 15 | 20 | 30 | 16 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-008 | Discovery & Governance | Annexure A security compliance assessment and control matrix | Design | RFQ Requirements + Statistics row 53 | 24 | 30 | 45 | 27 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-009 | Discovery & Governance | Project management, Agile ceremonies, RAID, status and stakeholder governance | PM | RFQ prefers Agile delivery | 60 | 80 | 100 | 70 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-010 | Discovery & Governance | Business change management and stakeholder communication plan | PM | Enterprise adoption | 15 | 20 | 30 | 18 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-011 | Platform Administration | User/role/permission matrix and user administration screens | Requirement | F-129 covers security but not detailed admin UX | 10 | 15 | 22 | 12 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-012 | Platform Administration | Workflow configuration and approval-matrix administration | Assumption | F-125 shared workflow engine | 14 | 20 | 30 | 16 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-013 | Platform Administration | Notification, reminder, escalation and email-template administration | Assumption | F-126/F-130/F-146 | 10 | 15 | 22 | 12 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-014 | Platform Administration | Document repository, metadata, versioning, preview, antivirus and retention | PM | Uploads across all modules | 18 | 25 | 38 | 20 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-015 | Platform Administration | File-ingestion monitoring, validation error queue, retry and reconciliation | Development | Excel/email/mass uploads | 18 | 25 | 38 | 20 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-016 | Platform Administration | Report and PowerPoint template management | AI/ML | Predefined and free-flow outputs | 14 | 20 | 30 | 15 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-017 | Platform Administration | Audit-log viewer, search, export and retention policy | Non functional | Audit trails exist but admin capability is absent | 12 | 18 | 25 | 15 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-018 | Platform Administration | Global search and indexing across structured records and documents | AI/ML | Central searchable platform | 12 | 18 | 28 | 14 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-019 | Platform Administration | Data retention, archive, legal hold and exit/data-portability export | Assumption | On-prem/data-transfer requirement | 10 | 15 | 24 | 13 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-020 | Data & Integration | Historical data profiling, cleansing, mapping and ownership sign-off | Assumption | RFQ row 36 | 22 | 30 | 50 | 26 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-021 | Data & Integration | Migration rehearsal/dry run and defect correction | Assumption | Historical pre-fill | 15 | 20 | 32 | 18 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-022 | Data & Integration | Production cutover migration, reconciliation and business sign-off | Assumption | Go-live readiness | 15 | 20 | 30 | 18 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-023 | Data & Integration | Sourcing system / EBON integration or governed secure file exchange | Assumption | F-006/F-024 | 22 | 30 | 45 | 26 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-024 | Data & Integration | ERP/SAP integration, error handling and reconciliation | Assumption | F-067 | 25 | 35 | 55 | 30 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-025 | Data & Integration | Inbound mailbox and outbound email integration, parsing and delivery tracking | Assumption | F-146 | 12 | 18 | 28 | 15 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-026 | Data & Integration | Commodity, forex and market-data feed integration | Assumption | Forecasting and automatic price calculation | 18 | 25 | 40 | 22 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-027 | Data & Integration | SSO/PKI integration testing, certificate lifecycle and fallback handling | Development | F-129 | 12 | 18 | 28 | 16 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-028 | Procurement Rules | Monday consolidated data-completion reminder and escalation after four reminders | Development | Outline Concept - Other than SRM step 5 | 5 | 8 | 12 | 6 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-029 | Procurement Rules | Buyer-material relationship master and mass upload | Development | Outline Concept step 10 / F-124 | 7 | 10 | 15 | 7 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-030 | Procurement Rules | Target EKL, effective-dated forecast price and car-volume mass upload | Development | Outline Concept step 15 | 12 | 18 | 28 | 13 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-031 | Procurement Rules | EBON PO mass-update file generation, validation and reconciliation | Development | Outline Concept step 13 | 10 | 15 | 25 | 12 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-032 | Procurement Rules | My Master Data / Department Master Data maintenance | Development | Outline Concept step 12 remark | 7 | 10 | 16 | 7 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-033 | Technical Change Rules | Daily consolidated buyer reminder from day 5 with aging count | Development | Outline Concept steps 6-7 | 5 | 8 | 12 | 6 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-034 | Technical Change Rules | Email delivery, rejection, resend and approval-note communication log | Development | Outline Concept step 12 | 7 | 10 | 16 | 8 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-035 | Technical Change Rules | Part-index-unchanged and AEKO-number linkage rules | Development | Outline Concept step 10 | 5 | 8 | 14 | 6 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-036 | Technical Change Rules | Supplier response channel implementation (portal vs buyer-upload model) | Clarification required | Scope changes materially by channel | 14 | 20 | 40 | 17 | Estimate after customer decision | Scope and effort change materially based on the selected operating model.
G-037 | SRM Rules | Monday SRM management-update reminder with Thursday due date | Development | Outline Concept - SRM step 3 | 4 | 6 | 10 | 5 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-038 | SRM Rules | Stakeholder-specific weekly alerts from six weeks and sample-receipt dependency | Development | Outline Concept - SRM steps 4-5 | 8 | 12 | 18 | 9 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-039 | SRM Rules | Configurable 19-milestone catalogue and part-level date override | Development | F-085/F-101 to F-104 | 14 | 20 | 30 | 15 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-040 | SRM Rules | Automatic SRM report email circulation and distribution-list management | Development | Outline Concept - SRM step 6 / F-116 | 5 | 8 | 14 | 6 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-041 | AI Governance & MLOps | Knowledge ingestion, RAG and vector-search foundation | AI/ML | AI assistant foundation | 25 | 35 | 50 | 29 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-042 | AI Governance & MLOps | Role-aware retrieval, source citations and permission filtering | AI/ML | Prevent unauthorized/unsupported responses | 18 | 25 | 38 | 22 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-043 | AI Governance & MLOps | NL-to-SQL semantic layer, query validation and guardrails | AI/ML | Structured price/cost queries | 22 | 30 | 45 | 25 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-044 | AI Governance & MLOps | AI evaluation dataset, accuracy thresholds and regression suite | AI/ML | AI acceptance and annual upgrades | 18 | 25 | 38 | 22 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-045 | AI Governance & MLOps | Prompt, model, version, approval and feedback governance | AI/ML | Vendor vs SAVWIPL model options | 14 | 20 | 30 | 18 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-046 | AI Governance & MLOps | Forecasting data pipeline, model training, back-testing and business sign-off | AI/ML | Commodity/forex/savings/delay models | 30 | 40 | 60 | 34 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-047 | AI Governance & MLOps | AI monitoring, model drift, usage and cost monitoring | AI/ML | Model maintenance and updates | 12 | 18 | 28 | 16 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-048 | Quality & Non-Functional | Test strategy, test plan, test cases and test-data management | QA | Project-wide QA | 18 | 25 | 38 | 20 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-049 | Quality & Non-Functional | Functional, system, integration and regression testing | QA | Project-wide QA execution | 70 | 90 | 120 | 75 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-050 | Quality & Non-Functional | Performance/load testing for concurrency and <30-second response target | QA | RFQ Requirements + Statistics rows 33-34 | 18 | 25 | 40 | 22 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-051 | Quality & Non-Functional | Security testing, VAPT, remediation and retest | Assumption | VW Group security | 22 | 30 | 45 | 27 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-052 | Quality & Non-Functional | Backup, restore, high availability and disaster-recovery design/test | Assumption | On-prem production readiness | 18 | 25 | 40 | 23 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-053 | Quality & Non-Functional | Browser, iPad, mobile, responsive and accessibility testing | Development | RFQ rows 15 and 42 | 14 | 20 | 30 | 17 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-054 | Quality & Non-Functional | AI accuracy, hallucination, authorization and adversarial testing | AI/ML | AI production readiness | 22 | 30 | 45 | 27 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-055 | DevOps & Operations | On-prem infrastructure sizing, provisioning, installation and hardening | AI/ML | On-prem deployment | 25 | 35 | 55 | 32 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-056 | DevOps & Operations | CI/CD, release management and Dev/Test/UAT/Prod deployment pipeline | Development | F-132 omits UAT and pipeline detail | 18 | 25 | 38 | 21 | Decompose/replace related feature; do not simply add | The capability is implied by an existing feature, but the delivery work and acceptance criteria are not visible.
G-057 | DevOps & Operations | Application monitoring, logging, SIEM integration and alerting | Development | Operational dashboard foundation | 18 | 25 | 40 | 22 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-058 | DevOps & Operations | Configuration, secrets, certificates, licences and dependency management | Assumption | Production operations | 10 | 15 | 24 | 13 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-059 | Training & Go-Live | End-user training delivery for all user groups | Development | RFQ rows 44-46; F-133 covers materials only | 18 | 25 | 40 | 23 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-060 | Training & Go-Live | Administrator, operations and support-team training / knowledge transfer | Development | Support handover | 10 | 15 | 24 | 14 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-061 | Training & Go-Live | Technical runbook, SOP, deployment, backup and support documentation | Assumption | Operational handover | 14 | 20 | 30 | 17 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-062 | Training & Go-Live | Cutover planning, go-live command centre and hypercare | Support | Four-month go-live target | 22 | 30 | 45 | 28 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.
G-063 | Training & Go-Live | 10x5 support model, SLA, incident/problem/change process and service desk setup | Support | RFQ rows 57-60 | 14 | 20 | 30 | 19 | Add as explicit project work package | Required for full-project delivery but absent from the current feature inventory.

## Estimate Assumptions
SAVWIPL AIS – Estimate Review Assumptions & Boundaries
Topic | Review Assumption / Guidance
Working Day | 1 person-day = 8 person-hours. The workbook has missing day values in rows 2–3 and an hour/day mismatch for F-145, so review totals are normalized from hours.
Current Estimate Boundary | The existing estimates appear to be feature-build estimates. They do not consistently show BRD, UX, architecture, QA, security, migration, DevOps, project management, training delivery, cutover or support setup.
Recommended Feature Estimate | Most-likely feature estimates include solution/detail design for the feature, development/configuration, code review, unit testing, developer integration testing and technical documentation.
Project-Level Work | Coverage Gaps contains delivery work packages that must be planned separately or explicitly decomposed from shared epics. Do not add all 'Partially covered' items without removing overlap.
Claude AI Assistance | Assumes enterprise use of Claude for analysis, code assistance, test generation and documentation. It does not materially reduce customer approvals, environment access, data cleansing, integration coordination, UAT or production support.
AI Saving Expectation | The current workbook implies approximately 33.6% saving. For the full enterprise lifecycle, a planning range of roughly 18–28% is more defensible until team maturity and reusable accelerators are demonstrated.
Scope Boundary | RFQ Management, Supplier Quotations/Comparison/Negotiation/Nomination and the separate Procurement Orders block are not clearly explicit in the RFQ baseline and should be confirmed as optional or included scope.
Shared Enablers | Master Data Core, Workflow Engine, Dashboards, AI Assistant, Notifications and Security are valid shared components. Module-level rows must represent incremental configuration, not a second full build.
Estimate Confidence | High = duplicate/error can be objectively identified. Medium = reasonable architectural estimate with open data/integration details. Low = scope or operating model is not confirmed.
Contingency | After BRD and technical discovery, apply 15–25% contingency to low-confidence integrations, AI/forecasting, migration, security and on-prem infrastructure items.
Timeline | A four-month go-live is feasible only as a tightly governed phased MVP with parallel workstreams, early infrastructure access, fixed templates, limited integration uncertainty and rapid customer sign-off.